# Week 9 Sprint 6 Progress Meeting Minutes

JobTrack Job Application Tracking System

| Date | 29 September 2026 | Duration | 1 hour |
| --- | --- | --- | --- |
| Location | Microsoft Teams | Sprint | Sprint 6, 22-29 September |
| Meeting type | Sprint progress review | Unit | Software Engineering Practice |
| Prepared by | Trinh Hieu Tran | Project | JobTrack |

# Attendees

| Team member | Student ID | Roles |
| --- | --- | --- |
| Trinh Hieu Tran | S394100 | Developer and Database Administrator |
| Pooja Tiwari | S396163 | Business Analyst and Report Analyst |
| Prince Kumar Sah | S388535 | Tester and Data Analyst |

# Meeting Purpose

The meeting reviewed Sprint 6 progress for the overdue follow-up dashboard, application summary dashboard and application archiving. The team checked completed work, identified the stories still in progress and agreed on the evidence required before closing the sprint.

# Agenda

- Review the status of all Sprint 6 Jira stories.

- Confirm the behaviour delivered for overdue follow-ups, dashboard statistics and archiving.

- Identify outstanding analysis, testing and documentation work.

- Agree on actions required before Sprint 6 closure.

# Sprint Progress Summary

At the meeting date, 5 of the 12 Sprint 6 work items were Done and 7 were In Progress. All three developer implementation stories were complete, while the remaining work focused on business-analysis confirmation, reporting, metric validation and final testing evidence.

| Feature | Completed | In progress | Current position |
| --- | --- | --- | --- |
| Overdue follow-ups | JOBTRACK-48 DA JOBTRACK-47 DEV JOBTRACK-49 TEST | JOBTRACK-29 BA JOBTRACK-50 RA | Rules, UI display and initial testing are complete. BA confirmation and feature documentation remain open. |
| Dashboard summary | JOBTRACK-56 DEV | JOBTRACK-30 BA JOBTRACK-57 DA JOBTRACK-58 TEST | The summary UI is implemented. Metric validation, acceptance confirmation and test evidence remain open. |
| Application archiving | JOBTRACK-59 DEV | JOBTRACK-31 BA JOBTRACK-60 TEST | Non-destructive archiving is implemented. Final acceptance review and archive-behaviour testing remain open. |

# Discussion Summary

1. The overdue follow-up display was demonstrated as complete. The team agreed that an overdue item must belong to the signed-in user, have a follow-up date earlier than the current date and still require action.

2. The dashboard summary was reviewed. Status totals must match the application list, remain isolated by user and update after an application is created, updated or archived.

3. Application archiving was confirmed as non-destructive. Archived records and documents must be preserved, removed from the active list and available through the archived view or filter.

4. The team noted that implementation alone does not complete a feature. Acceptance criteria, metric validation, test results, documentation and Jira evidence must also reflect the delivered behaviour.

# Decisions

- No additional feature scope will be added until the seven in-progress Sprint 6 items are completed or formally moved to the next sprint.

- Dashboard and archive calculations will use only the authenticated user's records.

- A story will move to Done only after its acceptance criteria, test evidence and relevant documentation are updated.

- Any defects identified during final testing will be assigned to the developer and retested before sprint closure.

# Action Items

| Owner | Action | Jira items | Due |
| --- | --- | --- | --- |
| Pooja Tiwari | Finalise acceptance criteria for the three features and complete the overdue-dashboard documentation. | 29, 30, 31, 50 | Before Sprint 6 closure |
| Prince Kumar Sah | Complete dashboard metric validation and attach dashboard and archive test results, defects and retest evidence. | 57, 58, 60 | Before Sprint 6 closure |
| Trinh Hieu Tran | Support clarification, resolve confirmed defects and ensure implementation evidence is linked to the completed developer stories. | 47, 56, 59 | Before Sprint 6 closure |
| All members | Review linked evidence, update Jira statuses and confirm whether any unfinished item must move to the next sprint. | Sprint 6 | Next group meeting |

# Next Meeting

The next group meeting will review the completed acceptance criteria, dashboard metrics, final test evidence and any defects requiring developer action before Sprint 6 is closed.